## Slide 1
Project Charter: UConn Student Retention Rate Analysis
Case for change / Problem Statement
UConn needs to improve the enrollment, attrition, and graduation rate of their undergraduate program. These two rates are pivotal indicators of both institutional effectiveness and overall success of students in higher education.
Business Case
Improving enrollment, attrition, and graduation rates makes for a more competent workforce, many of which might remain in Connecticut Better preparing students that will enroll in graduate school, likely also at UConn
In Scope | Out of Scope
Recommend better services be offered to students to assist with academics | Making assessments and recommendations for graduate students
Recommend better assistance with career guidance and networking for graduating students | Arranging a career fair for students
Recommend that the school offer mental health services | Setting up mental health services for students
Constraint Matrix |  |  | 
 | MOST | SOME | LEAST
SCOPE |  | ✓ | 
TIME | ✓ |  | 
COST |  |  | ✓
Top Risks (max. 5)
Failure to meet project deadline Inaccurate Data Limited availability of Software Poor communication within the team Bad cost estimation
Objectives / Goal statements
Integrate diverse datasets such as admissions, enrollment, and student surveys Identify factors influencing retention and graduation trends Develop predictive models to estimate student retention and graduation Formulate data-driven recommendations to improve retention and graduation
Assumptions
Our sponsors have provided us with sufficient data to begin our research Any additional data needed to achieve our goals is readily available to us There’s no major factors at the moment effecting university enrollment, attrition, or graduation rates
Project Costs (USD) |  | 
Total: | Internal: | External:
Project Benefits |  | 
NPV: | IRR: | Break Even:
Indirect Benefits: Enhanced Institutional Reputation, Improved Alumni Engagement and Support, More applicants |  | 

## Slide 2
Incoming Dependency | Outgoing Dependency
Signing the student NDA acknowledgment and submitting the FERPA training | Making recommendations to the university
Interaction and collaboration with Team members | Submitting final paper
Course overview and receive project data | Presenting our findings
Deliverables & Milestones (High Level Milestone Plan) |  |  | 
Project Start Date 08/28/2023 |  | Project End Date: 12/04/2023 | 
Key Deliverable | Milestone Name (MN) |  | Planned MS Date
Initial data exploration findings and understating the data | Data exploration |  | 09/11/2023
Cleaning the data and understanding the target variables and correlations | Data cleaning |  | 09/18/2023
Perform EDA to gain deeper understanding of the data | EDA |  | 09/25/2023
Use the most appropriate modeling technique /tool | Data Modeling |  | 10/09/2023
Use train and test data sets to to evaluate model performances | Model Training |  | 10/27/2023
Extract meaningful insights from the output of the model | Interpretation and Analysis |  | 11/06/2023
Present and report the results in a visual format | Visualization and Reporting |  | 11/20/2023
Progress review / adjustments | Progress Review |  | 11/27/2023
Comprehensive project report and recommendations for sustained improvement | Final Project Report |  | 12/04/2023
Signoff |  | 
Role | Signature | Date
Sponsor |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
PSB Member |  | 
Beneficiary |  | 
Project Organization | 
Sponsor | UConn BIPR
Steering Board Members (PSB) | Eric McKean
Project Manager | Saikrishna Bondalapati
Workstream Leaders | Deepak Pasala
Team Members | Rohit Reddy Marreddy, Siva Sobhan Prabhala, Bajram
Sponsor Liaison | Shriya Sudhakar Meshram
Project Charter: UConn Student Retention Rate Analysis